## Module-Reponsibility
# | Module | Developer | Tester | Test Status | Documentation | Comments
1 | Dashboard | Sumon | Millat | In Progress
2 | Relationships | Sumon | Sabbir | In Progress
2.1 | - Customers | Sumon | Sabbir | In Progress
2.2 | - Suppliers | Sumon | Sabbir
2.3 | - Team Members | Sumon | Sabbir
3 | Items | Sumon | Millat
4 | Point of Sale (POS) | Millat | Sumon
5 | Sales | Sabbir | Sumon
5.1 | - Qoutations | Sabbir | Sumon
5.2 | - Invoices | Sabbir | Sumon |  | Invoice
5.3 | - Payments | Sabbir | Sumon
6 | Purchases/Stocks | Sabbir | Millat
6.1 | - Purchases | Sabbir | Sabbir
6.2 | - Purchases Receive | Sabbir | Sabbir
6.3 | - Payments | Sabbir | Sabbir
6.4 | - Stock Transfers | Sumon | Sabbir
6.5 | - Stock Adjustments | Sumon | Sabbir
7 | Bank & Transactions | Sabbir | Millat
7.1 | - Bank Accounts | Sabbir | Millat
7.2 | - Bank Accounts Deposites | Sabbir | Millat
7.3 | - Bank Accounts Transfer | Sabbir | Millat
7.4 | - Transactions | Sabbir | Millat
8 | Projects | Sabbir | Millat |  | Project
9 | Tasks | Sabbir | Millat
10 | Time Sheets | Millat | Nobeul
11 | Tickets | Sabbir | Millat
12 | Calender | Sumon | Nobeul
13 | Expenses | Millat | Nobeul
14 | Leads | Millat | Nobeul
15 | Reports | Sumon | Sabbir
15.1 | - Inventory Stockt on Hand | Sumon | Sabbir
15.2 | - Sales Repot | Sumon | Sabbir
15.3 | - Purchase Report | Sumon | Sabbir
15.4 | - Expenses Report | Sumon | Sabbir
15.5 | - Income Report | Sumon | Sabbir
15.6 | - Income VS Expense | Sumon | Sabbir
15.7 | - Leads Report | Sumon | Nobeul
16 | Settings | Nobeul
16.1 | - Company Details | Nobeul | Sumon
16.2 | - Company Settings | Nobeul | Sumon
16.3 | - Finances | Nobeul | Sumon
16.4 | - Email Template | Nobeul | Sumon
16.5 | - SMS Template | Nobeul | Sumon
16.6 | - Preference | Nobeul | Sumon
16.7 | - Print Barcode/Level | Nobeul | Sumon
17 | Cutomer Panel | Sabbir | Sumon
| - Qoutations | Sabbir | Sumon
| - Invoices | Sabbir | Sumon
| - Payments | Sabbir | Sumon
| - Supports | Sabbir | Sumon
| - Projects | Sabbir | Sumon

## Task Status Work Flow
Not Started | In Progress | Testing | Complete | On Hold | Re-Open
In Progress | Testing | Complete | Re-Open | In Progress | On Hold
Complete | Complete | Not Started |  | Testing | Testing
Testing | On Hold | In Progress |  | Complete | Complete
On Hold | Not Started | On Hold |  | Not Started

## ChangeLog
version 1.0
Released Date -
Bugs Fix | Improments | New Features
Lorem ipsum, or lipsum as it is sometimes known | Lorem ipsum, or lipsum as it is sometimes known | Lorem ipsum, or lipsum as it is sometimes known
Lorem ipsum, or lipsum as it is sometimes known | Lorem ipsum, or lipsum as it is sometimes known | Lorem ipsum, or lipsum as it is sometimes known
Lorem ipsum, or lipsum as it is sometimes known | Lorem ipsum, or lipsum as it is sometimes known
Lorem ipsum, or lipsum as it is sometimes known | Lorem ipsum, or lipsum as it is sometimes known
Lorem ipsum, or lipsum as it is sometimes known
Lorem ipsum, or lipsum as it is sometimes known
Lorem ipsum, or lipsum as it is sometimes known

## New Features
Feature Name | Feature Description | Priority | Status | External Link
Application Activity | There will be whole activity of application. Then all acitivity will separated for individual model. Like Task activity, Invoice activity, Banking and Transaction acitivity, Project acitivity etc. | HIGH | Not Started
Dynamic PDF export | There will be only one PDF export template, From that template all template will get design and layout like expense, ticket, task, invoice etc. | HIGH | Not Started
More Variable for Email template | Need more variable in email template module like company address, company logo URL etc in every email template | MEDIUM | Not Started
Task Details Modal Design | Task details modal redesign, it will be like trello task details (Not exactly like that, but looks and feels will be like trello task modal details) | HIGH | Not Started
Project Setting (For Delete Project) | There will be three option of deleting project. #1 - Project will not be deleteable if task, invoice etc exist. #2 - Project will be deleteable and exiting task, invoices etc also be deleteable. #3 - Project will be deletable but task, invoices will not be deleteable (There will '-' if project not exist.) | MEDIUM | Not Started
Tickets Settings (Edit ticket for customer and team member) | There will be a tickets settings option where admin can eanble or disable that customer and team member ticket reply can edit or not. | MEDIUM | Not Started
Activities | Whole system activities will be recorded. For example John Doe logged in system, then activity will be recorded that “John Doe logged in at 2.03pm”. Same activity will be recorded when someone also logged out. | HIGH | Not Started | View Documentations
Time sheet (Improvement) | Right now we can add timer list from task -> task details modal. But if there is lots of time sheet for a task then it will be dificult to manage all time sheet list. That's there will be a option in timesheet module for adding or modifying timesheet. | MEDIUM | Not Started